## Slide 1: DailyDutch
Free daily Dutch lessons for newcomers — a project from idea to launch
Tobbisch Amiri · Project Management · SRH Haarlem University of Applied Sciences
15 – 31 October 2026 · dailydutch.vercel.app
Notes: Introduce yourself and the project in one sentence: DailyDutch is a free website that teaches Dutch from zero to everyday level in 120 short daily lessons. I ran this project alone, from 15 to 29 October, and I'll walk through it the way we studied: charter, scope, stakeholders, plan, risks, testing and launch, and closure.

## Slide 2: Project charter
Why this project
International students and newcomers need everyday Dutch fast. Most apps cost money, need an account, or use words the learner has never seen.
Goal
A free website with one short Dutch lesson per day — no login, no ads.
Project manager
Tobbisch Amiri (solo)
Sponsor
Course lecturer, SRH Haarlem
Timeline
15 – 29 October 2026
Budget
€0 (free tools and hosting)
SMART objectives (all by 29 Oct)
120 daily lessons, beginner to A2 level
Every sentence uses only words already taught
Built-in review so words are remembered
Works on a phone, also offline
Online and free for everyone
Notes: The charter is the one-page agreement that started the project. The business case: newcomers need Dutch quickly, and most apps cost money, need an account, or use words you haven't learned yet. Objectives were set SMART: 120 lessons, only already-taught words, a review system, works on a phone, and online for free — all by 29 October with zero budget.

## Slide 3: Scope: in and out
In scope
120 daily lessons: words, grammar, conversation
Review of learned words (spaced repetition)
Personal word list and daily streak
Listen to Dutch pronunciation
Use on phone, also offline
Testing and public launch
Out of scope
User accounts
Payments or ads
App-store apps
Advanced levels (B1+)
Teacher dashboards
Notes: Writing down what is out of scope protected the two-week timeline. Accounts or a mobile app store version would need servers, privacy work and money — so they were explicitly excluded and parked as ideas for later.

## Slide 4: Stakeholders: power × interest
Keep satisfied
Hosting provider
Stay within the free plan
Manage closely
Course lecturer (sponsor)
Updates, approval, sign-off
Monitor
Open-data sources (word lists)
Correct credit to the source
Keep informed
Learners, classmates, test users
Try the app, give feedback
Power ↑
Interest →
Notes: The lecturer has high power and high interest, so I managed that relationship closely with updates and the final sign-off. Learners and test users have high interest but low power: I kept them informed and collected their feedback during testing. The hosting provider and the open-data sources: keep satisfied and monitor — stay within the free plan and credit the sources.

## Slide 5: How I worked: method and roles
Method: iterative, Agile-style
Build a small working version first (MVP): lesson format, 3 lessons, review
Then grow in small steps: more lessons, audio, phone use
MoSCoW priorities to keep scope under control
Progress tracked in PLAN.md (Done / Next) and Git commits
One person, four roles
Project manager
Plan, schedule, risks, reporting
Developer
App, tooling, tests, deployment
Content author
120 lessons, word list, Dutch quality
Tester
Automatic checks, read-through, real use
Feedback from: course lecturer (sponsor), classmates and test users

## Slide 6: Plan and schedule: 15 – 29 October
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
October
Initiation: idea, charter
Planning: scope, stakeholders, risks
Design: lesson format and structure
Build first version + first lessons
All 120 lessons, audio, phone use
Testing
Launch (deployment)
Closure: presentation, sign-off
Milestones: charter 15 Oct · first version 24 Oct · tested 27 Oct · live planned 28 Oct, actual 31 Oct (+3 days)
Notes: The work was split into eight phases over fifteen days. Planning came first, then a small working version to prove the idea, then the full content, then a full testing day before going live on 28 October. The last day is closure: this presentation, lessons learned and sign-off. Everything was delivered on schedule.

## Slide 7: Risk management
Risk | Score | Response
Not finished in two weeks (one-person team) | High | Small first version, then expand; fixed daily plan
Language mistakes in the lessons | High | Automatic word check + full read-through on test day
Scope creep (accounts, apps, more levels) | Medium | Clear out-of-scope list, ideas parked for later
Learners lose progress on a new device | Medium | Accepted: no accounts by design, explained to users
Launch problems with hosting | Low | Free, simple hosting; can move to another host in minutes
Score = probability × impact. All risks had an owner (Tobbisch Amiri) and were reviewed daily.
Notes: Risks were scored on probability times impact, from 1 to 5 each. The two biggest — running out of time as a one-person team, and mistakes in the Dutch — were handled with a small first version and a dedicated testing day. Being a solo project was itself a risk: no backup person, so the plan kept a buffer day for testing.

## Slide 8: What I built
01
Daily lesson
Words → grammar → dialogue, with exercises
02
Review
Spaced repetition so words stick
03
Home
Today's lesson, words due, daily streak
04
My words
Add your own words to the review
05
Listen + Sounds
Dutch voice and a pronunciation page
06
Works offline
Install on phone, no login needed
Live demo
dailydutch.vercel.app
Open it on any phone or laptop. No login, no ads, free.
Demo: today's lesson → exercise → listen → review

## Slide 9: Testing and launch
Testing · 27 Oct
Automatic check: every lesson uses only words already taught
Read-through of all 120 lessons for language and story
Real-use test on phone and laptop; small fixes made
Launch · 31 Oct (planned 28 Oct)
Live at dailydutch.vercel.app (Vercel, free hosting)
Every saved update goes live automatically
Learners open one link — no login, can install on phone
120
lessons
1,822
words
0
untaught-word errors
€0
cost
Notes: Quality was checked in three ways: an automatic check that blocks any lesson using a word that wasn't taught yet, a full read-through of the lessons, and a day of real use on phone and laptop. On 28 October the website was published on Vercel, a free hosting service: every update I save is published automatically. Learners simply open the link, and can add it to their phone's home screen.

## Slide 10: Closure: results and lessons learned
5 / 5
objectives met
live 3 days late · €0 budget
Definition of Done complete
Keep doing
Start small, then grow
Write down what is out of scope
Automate the key quality rule
Do better
Test with real users earlier
Go live early, not at the end
Charter and risks before any work
Dank je wel — questions? · dailydutch.vercel.app
Notes: All five objectives were met on time and within the zero budget, and the Definition of Done is complete: built, tested, live and presented. What I'd keep: start small, write down what's out of scope, and automate the most important quality rule. What I'd change: test with real users and go live earlier instead of at the end, and write the charter and risk list before starting the work.