## Slide 1: DailyDutch
Free daily Dutch lessons — from project charter to (almost) done
Project Management · SRH Haarlem University of Applied Sciences
[Team names] · [Presentation date]
Notes: Introduce the team and the project in one sentence: DailyDutch is a free web app that teaches Dutch from zero to A2 in 120 daily lessons. Today we walk through the whole project life cycle: initiation, planning, execution, monitoring and closure.

## Slide 2: Agenda
1
Initiation
Problem, business case, project charter
2
Planning
Scope, stakeholders, WBS, schedule, risks
3
Execution
What we built and how
4
Monitoring & control
Quality, results, Definition of Done
5
Closure
Lessons learned, deployment, next steps
Notes: We follow the project life cycle. Initiation and planning documents were the baseline; execution and monitoring show how we built and controlled the work; closure shows where we stand against the Definition of Done.

## Slide 3: Learning Dutch should not cost money or patience
The problem
Most apps need subscriptions or accounts
Sentences use words the learner never saw
Words are learned once, then forgotten
No clear daily rhythm
Our solution: DailyDutch
Free, no login, no ads
Only words already taught — checked by a script
Spaced-repetition review built in
One 10–15 min lesson per day, 120 days
Notes: Business case. Newcomers and international students need everyday Dutch fast. Most apps are paid, need an account, or use sentences full of words you haven't learned. Our idea: one short lesson per day, and every sentence only uses words you already know.

## Slide 4: Project charter: five SMART objectives
O1
Complete A1–A2 curriculum
Target: 120 lessons
Met
O2
Only already-taught words
Target: 0 validator errors
Met
O3
Long-term retention
Target: Spaced-repetition review
Met
O4
Phone + offline
Target: Installable PWA
Met
O5
Public and free
Target: Live on Vercel
Open
Budget €0 · Constraint: no backend, all progress stays in the learner's browser · Sponsor: course lecturer
Notes: These are the objectives from the charter. Four of five are met today; O5, the public deployment, is the main open item and is why the Definition of Done is not yet fulfilled.

## Slide 5: Scope: what we build — and what we don't
In scope
120 lessons: words, grammar, dialogue
Lesson flow + exercises
Spaced-repetition review
My words, home dashboard, streak
Pronunciation page + listen buttons
PWA: install on phone, offline
Content tooling, tests, deployment
Out of scope
Accounts / sync
Payments, ads
Native apps
B1 and higher
Human audio
Teacher dashboards
Notes: Writing down out-of-scope items was our main defence against scope creep. Accounts and sync were tempting but would need a backend, privacy work and cost.

## Slide 6: Stakeholders: power × interest
Keep satisfied
Hosting provider (Vercel)
Stay within free tier
Manage closely
Lecturer / examiner (sponsor)
Status updates, sign-off
Monitor
Open-data providers
CC BY-SA attribution
Keep informed
Learners, classmates, test users
Live link, feedback
Power ↑
Interest →
Notes: The lecturer has high power and high interest, so we manage them closely with status updates. Learners and test users have high interest but low power: keep informed and ask for feedback. Data providers and Vercel: monitor and keep satisfied — attribution and fair use.

## Slide 7: Work breakdown structure
1 DailyDutch
1.1 PM
Charter, plan, risks, reporting, closure
1.2 Setup
Toolchain, Git + GitHub
1.3 Content system
Format, validator, word list, guide
1.4 Lessons
1–3, 4–30 (A1), 31–120 (A2), read-through
1.5 Application
Lesson, review, my words, home, speech, PWA
1.6 Quality
Unit tests, build gate, daily use test
1.7 Release
Deploy to Vercel, smoke test
Full WBS tree: project-management/02-project-plan.md
Notes: We split the work into seven packages. Content system and lesson content were the biggest; the content system (validator, word list, guide) made the 120 lessons possible in a short time.

## Slide 8: Schedule: milestones planned vs. reached
M1
19 Oct
Setup
M2
24 Oct
MVP + lessons 1–3
M3
25 Oct
Lessons 4–120
M4
25 Oct
PWA + audio
M5
[date]
Read-through + daily test
M6
[date]
Deploy on Vercel
M7
[date]
Present + sign off
● reached ○ remaining
Notes: Build went fast: setup on 19 October, the MVP on the 24th and all 120 lessons plus PWA and audio on the 25th. What is left is quality review, deployment and closure. Fill in the planned dates from your original plan.

## Slide 9: Risk management: top risks and responses
Risk | P×I | Response | Status
R1 Dutch errors in lessons 4–120 | 16 | Read-through by Dutch speaker | Open
R4 Not finished before deadline | 15 | MVP first, tooling for speed | Mostly closed
R3 Scope creep (accounts, sync…) | 12 | Out-of-scope list, MoSCoW | Controlled
R2 Sentence uses untaught word | 9 | Validator in build | Closed
R6 Learner loses browser progress | 9 | Accepted, explained | Accepted
R7 Deployment / hosting fails | 8 | Static build, any host works | Open
Scale 1–5 for probability (P) and impact (I). Full register with 10 risks: 03-risk-register.md
Notes: We scored risks on probability times impact. The highest risk now is language quality in the fast-written lessons, so the read-through is on the remaining-work list. The 'unknown word' risk was closed by automation: the build fails if any sentence breaks the rule.

## Slide 10: What we built
1
Daily lesson
Words → grammar → dialogue, with gap-fill exercises
2
Review
Spaced repetition: 8 boxes, 1 to 60-day gaps
3
Home
Today's lesson, words due, streak, words known
4
My words
Add your own words to the review
5
Listen + Sounds
Dutch speech voice; pronunciation rules page
6
Works offline
Install on phone (PWA), no login, no backend
Notes: Short tour of the app — this is a good moment for a live demo. Every lesson goes words, grammar, dialogue. Review uses Leitner boxes: correct answers move a word up a box with a longer gap, up to 60 days; a wrong answer sends it back to box 1.

## Slide 11: How we built 120 lessons fast and safely
1
Open data
Frequency list + Wiktionary → word list with articles, plurals, verb forms
→
2
Coverage
Script picks the most frequent words not yet taught
→
3
Write
Authoring guide + 3 reference lessons set tone and format
→
4
Validate
Build fails if any sentence uses an untaught word
Tech: Vite + React + TypeScript · Vitest · static site · data CC BY-SA 4.0
Notes: Process: build a vocabulary list from open data ordered by frequency, use the coverage script to pick the next words, write the lesson following the authoring guide, and let the validator check it. The first three lessons were hand-written as the reference standard.

## Slide 12: Results in numbers
120
lessons (A1–A2)
1,822
words taught
660
grammar exercises
1,436
dialogue lines
0
validator errors
€0
total cost
Notes: All numbers come straight from the repository on 28 October: validator output, test run and a count over the lesson files.

## Slide 13: Quality control: automated gates + human review
Check | Tool | Result
Known-words-only rule | npm run check | 120 lessons OK
Unit tests (SRS, dates, answers) | npm test (Vitest) | 7 / 7 pass
Type safety | tsc --noEmit | Pass
Build gate | npm run build | Pass
Language + story review | Human read-through | Pending
Real-life use | Daily use test | Pending
Notes: Quality is controlled at three levels. The build gate runs content check, type check and build in one command, so a broken lesson can never be shipped. The human read-through is still open — that's the gap automation can't close.

## Slide 14: Definition of Done: 7 of 13 criteria met
54%
Done
✓ 120 lessons with words, grammar, dialogue
✓ Validator: 0 errors
✓ Unit tests pass
✓ Type-check + build pass
✓ All pages work
✓ PWA installable + offline
✓ Code in Git + GitHub
Remaining
☐ Read-through lessons 4–120
☐ Daily use test + fixes
☐ Deployed on Vercel
☐ Live smoke test (desktop + phone)
☐ PLAN.md updated
☐ Documents + sponsor sign-off
Notes: Honest status: the product is built, but the project isn't done yet. Six criteria remain, all in review, deployment and sign-off. This is why we don't call the project closed today.

## Slide 15: Lessons learned
Keep doing
Build a thin MVP first, then scale
Automate the rule that matters most
Reuse open data before writing by hand
Document the process (authoring guide)
Write down what is out of scope
Do better next time
Deploy early and continuously
Plan review time per batch of content
Baseline planned dates at kickoff
Get test users in week 1
Write charter + risks before coding
Notes: Biggest wins: MVP first, automate the key quality rule, and write down what is out of scope. Biggest improvements: deploy early instead of at the end, plan review time while writing content, and baseline the schedule at kickoff.

## Slide 16: Next steps to close the project
1
Review
Read-through lessons 4–120, fix Dutch + story
[Owner] · [date]
2
Test
Daily use test, fix annoyances
[Owner] · [date]
3
Deploy
Vercel: Vite preset, npm run build → dist
[Owner] · [date]
4
Close
Live smoke test, update PLAN.md, sponsor sign-off
[Owner] · [date]
Notes: Four steps to meet the Definition of Done. Deployment itself is small: Vercel builds the Vite app from GitHub with npm run build and serves the dist folder. Then we smoke-test on desktop and phone and ask the sponsor to sign off.

## Slide 17: Dank je wel!
Questions? · Live demo: [live URL after deployment]
Notes: Thank the audience. Offer a live demo on a phone if time allows. 'Dank je wel' is the very first phrase from lesson 1.